## Sheet1
Risk ID | Risk Title | Description | Likelihood | Impact | Severity | Risk Owner | Mitigation | Status
RS-1001 | Poor Vendor Risk Management | Inadequate vendor assessment leading to sensitive data exposure | Medium | High | Medium | GRC/Management | Risk Assesment Framework, Require ISO 27001 Certification, Annual review | In Progress
RS-1002 | AI Model Bias | Biased AI algorithms creates risks for fines and reputational damage | Medium | Medium | High | Data Scientist | Fairness Audits in Model Training, Require HITL Validation Before Deployment | Planned
RS-1003 | Misconfigured Cloud Storage | Insecure cloud platforms from misconfiguration, violating compliance standards | High | High | High | Sys Admin/Cloud Engineer | Implement IaC With PaC Validation, Cloud Configuration Scanning | Mitigated (Ongoing Monitoring)
RS-1004 | 3rd Party API Dependency | Relying on Third Party API risk vulnerabilites and service disruptions | High | Medium | Medium | DevOps/Software Engineer | Due Diligence Before Integration, Monitor API Performance, Implment API Gateway | Not Started
RS-1005 | Data Privacy Compliances | Rapid expansion and data intake spark privacy compliance concerns | Medium | High | High | GRC/Compliance Officer | Conduct Regular PIAs, Implement RBACs, Data Retention Policy, GDPR/CCPA | In Progress